## Cover Page
Clinical Safety Hazard Log - Interweave Exchange aka SoS
Programme | YHCR SoS
Sub-Prog / Project | Clinical Safety
Prog. Director | Lee Rickles | Status | Complete
Owner | Paul Warwick | Version | 0.4
Author | Paul Warwick | Version Date | 18.09.2023
Document Purpose
To provide the Hazard Log for all on-boarding and current on-boarded sites. Share visibility of the Hazards that may be relevant to their organisation. This provides the hazards for SoS, gives examples of some generic Hazards which may be relevant to both providers and consumers. Please Note: These may change over time and will be updated where possible, always refer to the YHCR's CSO for the latest version for each organisation.

## SoS Hazard Log
| Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[5 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
1 | SoS does not receive data from providing system. | Clinician at consuming side is unable to view any additional patient information. | The patient will not receive the appropriate level of care due to the information not been available at the time to the clinician | 1. Providing systems are not aware if the message(s) has been sent successfully | Please Refer to the SoS Hazard Log tabbed below for the individual message type design descriptions.: 1- Synchronous Query 3-Subscriptions 4-Transacational Messaging. |  | On-boarding sites must follow a set specification from both Synanetics and the YHCR Programme Team to ensure they are capable of providing/consumer or in some cases both the data of patients. Within this included is support from the technical and design architects, the project and business analysts. Communication support and also business change is mentioned and advised. This is however the organisations responsivity. | Various Tasks must be completed prior to joing- technical, IG, Cyber, Communication, UAT, Tests in Test and Clinical Assurance | Various Business Process meetings are held between the organisations, the YHCR Programme and Synananetics | Minutes of the meetings held are recorded. Meetings take place regularly. Various groups are embedded- Clinical and Technical Design Authority group. Change Advisory Board etc. | The severity of the hazard cannot be scored as the severity will alter between sites/users. It is therefore the responsibility of the provider/consumer to evaluate the hazards based on their environment and uses of the system. |  |  |  | Additional Controls should be added by the provider/consumer, these should be relevant to your own organisation. | [5 empty] | The severity of the hazard cannot be scored as the severity will alter between sites/users. It is therefore the responsibility of the provider/consumer to evaluate the hazards based on their environment and uses of the system. |  |  |  | Rebecca Wilson | Transferred
|  |  |  | 2. System/connection failure at provider site | [20 empty] | Rebecca Wilson | Transferred
|  |  |  | 3. System/connection failure of SoS | [20 empty] | Rebecca Wilson | Transferred
2 | Data within the message sent by the provider and received by SoS incorrect | Clinician at consuming side bases the treatment decision on incorrect information | Incorrect information could lead to patient harm or death if the information is received incorrectly as the clinician could base their clinical decision and treatment on the information provided. | 1. Corruption in message between provider and SoS | [20 empty] | Rebecca Wilson | Transferred
|  |  |  | 2. Incorrect configuration / mapping | [20 empty] | Rebecca Wilson | Transferred
3 | There is a delay to SoS receiving the message from the provider | There is a delay to the clinician at the consuming side receiving any information | Delay in the information been received could lead to a delay in the patients care | 1. System/connection failure at provider site | [20 empty] | Rebecca Wilson | Transferred
|  |  |  | 2. System/connection failure of SoS | [20 empty] | Rebecca Wilson | Transferred
[25 empty] | Rebecca Wilson | Transferred

## 1Synchronous Query
Hazard | [5 empty] | Initial Risk Rating |  |  | Additional Controls |  |  |  | Residual Hazard Risk Rating
Num | Hazard Name | Hazard Description | Potential Clinical Impact | Possible Causes | Existing Controls | Consequence | Likelihood | Risk | Design | Test | Training | BPC | Consequence | Likelihood | Risk | Summary of Actions | Owner | Status
1.1 | Service is Unavailable, or Access is Denied | A data consumer is either unable to connect to the System of Systems or their connection is rejected. Care professionals are unable to access data about their patient or client which is held by care settings other than their own | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians will revert easily to previous ways of working. Client software will be aware of a dropped connection and will be able to inform clinicians that a fault has occurred. Clinicians will be able to distinguish no data being available from a fault preventing access. | a hardware or software fault results in system unavailability | Software components are hosted in a virtualised environment on hardware with inbuilt redundancy. The hypervisor provides for high availability and will automatically re-instantiate non-functional components. Components are monitored and a service desk automatically informed of a range of conditions. Service availability could be monitored using an external arbiter if a use case were to justify it. Faults are logged and it is possible to establish the root cause of a failure. | Minor | Medium | 2 |  | Service availability could be monitored using an external arbiter if a use case were to justify it. |  |  | Minor | Low | 1 |  | All | Open
1.2 | Service is Unavailable, or Access is Denied | A data consumer is either unable to connect to the System of Systems or their connection is rejected. Care professionals are unable to access data about their patient or client which is held by care settings other than their own | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians will revert easily to previous ways of working. Client software will be aware of a dropped connection and will be able to inform clinicians that a fault has occurred. Clinicians will be able to distinguish no data being available from a fault preventing access. | data is corrupted through faulty disks or a software error to an extent that is causes a loss of service | Components are designed to be stateless where possible with few dependencies on data. Exceptions are configuration data, the master patient index, consent policies, master records for patient, practitioners and organisations. A copy of configurations is held in a source control repository and other data is backed up daily. A backup can be restored within two hours. Master data can be recreated by replaying messages from participants and other sources. . | Minor | Medium | 2 |  | Service availability could be monitored using an external arbiter if a use case were to justify it. |  |  | Minor | Low | 1 |  | All | Open
1.3 | Service is Unavailable, or Access is Denied | A data consumer is either unable to connect to the System of Systems or their connection is rejected. Care professionals are unable to access data about their patient or client which is held by care settings other than their own | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians will revert easily to previous ways of working. Client software will be aware of a dropped connection and will be able to inform clinicians that a fault has occurred. Clinicians will be able to distinguish no data being available from a fault preventing access. | a DNS, firewall configuration change or a certificate revocation denies access to an individual participant. | Firewall and certificate changes are controlled by a Change Advisory Board. Certificate signing and revocation is software controlled and audited. Only privileged system administrators are able to revoke a certificate. Mutual TLS authentication is not operational. A participant will not be denied access because of a DNS entry. | Minor | Very Low | 1 |  | Service availability could be monitored using an external arbiter if a use case were to justify it. |  |  | Minor | Very Low | 1 |  | All | Open
1.4 | Service is Unavailable, or Access is Denied | A data consumer is either unable to connect to the System of Systems or their connection is rejected. Care professionals are unable to access data about their patient or client which is held by care settings other than their own | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians will revert easily to previous ways of working. Client software will be aware of a dropped connection and will be able to inform clinicians that a fault has occurred. Clinicians will be able to distinguish no data being available from a fault preventing access. | a software update introduces a fault. | Software changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan. Software is subjected to continuous integration testing which highlights regressive behaviour. Software source code is maintained in a public source code repository. Problematic changes can be easily backed out. | Minor | High | 2 | Maintenance is controlled by a Change Advisory Board | Service availability could be monitored using an external arbiter if a use case were to justify it. |  |  | Minor | Medium | 2 |  | All | Open
1.5 | Service is Unavailable, or Access is Denied | A data consumer is either unable to connect to the System of Systems or their connection is rejected. Care professionals are unable to access data about their patient or client which is held by care settings other than their own | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians will revert easily to previous ways of working. Client software will be aware of a dropped connection and will be able to inform clinicians that a fault has occurred. Clinicians will be able to distinguish no data being available from a fault preventing access. | planned maintenance results in downtime. | Maintenance is controlled by a Change Advisory Board Any maintenance requiring downtime will be scheduled outside of peak operational hours | Minor | Very High | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Minor | Very High | 3 |  | All | Open
1.6 | Service is Unavailable, or Access is Denied | A data consumer is either unable to connect to the System of Systems or their connection is rejected. Care professionals are unable to access data about their patient or client which is held by care settings other than their own | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians will revert easily to previous ways of working. Client software will be aware of a dropped connection and will be able to inform clinicians that a fault has occurred. Clinicians will be able to distinguish no data being available from a fault preventing access. | an erroneous consent policy denies access to all data to an individual participant | During this phase consent policies are likely to be simple and binary: to allow all data or no data in a given context. The potential for mistake is low, Policies will be applied by a system administrator who has been trained in the potential for impacting service availability. | Minor | Very Low | 1 | Software changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan; Software changes move through a staging environment prior to application to live. The staging environment has data which is representative of live and endpoint simulators which replicate the behaviour of data providers | Software is subjected to continuous integration testing which highlights regressive behaviour. |  |  | Minor | Very Low | 1 |  | All | Open
2.1 | Query Results are Corrupted | Data returned from the System of Systems to a data consumer are not reflective of data supplied by data providers. | Clinicians are making decisions based on data returned by the System of Systems. Data corruption may be subtle and undetectable by the clinician. The wrong decision could adversely impact the care of a patient. Use of the System-of-Systems is limited to 5 participants and the impact will be localised. | Possible cause: a software fault corrupts FHIR resources in transit. | Corruption to the structure of FHIR resources will result in them being unreadable by client software. Guidance provided to data consumers recommends that the end-user is informed of detectable data errors so reducing the possibility of misinformed decision. FHIR resources can optionally be validated against schemas and coding systems prior to release by the System of Systems. Validation is enabled after any software upgrade or after onboarding a participant. Software is coded to a design which minimises manipulation for resource content to a few essential operations. | Major | Low | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Major | Low | 3 |  | All | Open
2.2 | Query Results are Corrupted | Data returned from the System of Systems to a data consumer are not reflective of data supplied by data providers. | Clinicians are making decisions based on data returned by the System of Systems. Data corruption may be subtle and undetectable by the clinician. The wrong decision could adversely impact the care of a patient. Use of the System-of-Systems is limited to 5 participants and the impact will be localised. | : deduplication rules cause references to local resource to be replaced with a reference to a regional resource representing a different concept | Only patients, practitioner and organisation references are deduplicated. Deduplication is made on a deterministic basis (i.e. a simple identifier is used to determine resource equivalence). This is simple to test, and behaviour is predictable. Automated tests validate regional resource references for 100+ sample queries aligned with wave 1 use cases. | Significant | Low | 2 | Software is coded to a design which minimises manipulation for resource content to a few essential operations | FHIR resources can optionally be validated against schemas and coding systems prior to release by the System of Systems. Validation is enabled after any software upgrade or after onboarding a participant. |  |  | Significant | Low | 2 |  | All | Open
3.1 | Query Results are Incomplete | A result set returned to a data consumer is missing data items which are known to one or more data providers. | Clinicians are making decisions based on information returned by the System of Systems. An absence of data may cause an incorrect decision to be made with consequences for the patient. However, participation in the YHCR is limited to 5 organisations, data available is inherently incomplete, and this will be known to users. No reliance will be made on data completeness. | a data provider is inaccessible due to a network failure or other technical problem and no data can be obtained from this source for a period of time. | The System-of-Systems inserts information into the result set returned to the data consumer detailing that the data provider is unavailable. Client software can inform users that data is missing from potential sources. Guidance provided to data consumers recommends that the end-user is informed of reported data quality issues so reducing the possibility of misinformed decision. Connectivity is monitored and a service desk automatically informed if a connection is unavailable for an extended period. | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
3.2 | Query Results are Incomplete | A result set returned to a data consumer is missing data items which are known to one or more data providers. | Clinicians are making decisions based on information returned by the System of Systems. An absence of data may cause an incorrect decision to be made with consequences for the patient. However, participation in the YHCR is limited to 5 organisations, data available is inherently incomplete, and this will be known to users. No reliance will be made on data completeness. | a data provider supplies only subset of data known to the care provider. For example, data may be available for only a subset of services performed. | Wave 1 participants are going live with point to point use cases for which data availability has been established as a prerequisite. | Significant | Low | 2 |  |  |  |  | Significant | Low | 2 |  | All | Open
3.3 | Query Results are Incomplete | A result set returned to a data consumer is missing data items which are known to one or more data providers. | Clinicians are making decisions based on information returned by the System of Systems. An absence of data may cause an incorrect decision to be made with consequences for the patient. However, participation in the YHCR is limited to 5 organisations, data available is inherently incomplete, and this will be known to users. No reliance will be made on data completeness. | a software fault leads to data being lost in transit. | Automated tests validate regional resource references for 100+ sample queries aligned with wave 1 use cases | Significant | Low | 2 |  |  |  |  | Significant | Low | 2 |  | All | Open
3.4 | Query Results are Incomplete | A result set returned to a data consumer is missing data items which are known to one or more data providers. | Clinicians are making decisions based on information returned by the System of Systems. An absence of data may cause an incorrect decision to be made with consequences for the patient. However, participation in the YHCR is limited to 5 organisations, data available is inherently incomplete, and this will be known to users. No reliance will be made on data completeness. | an erroneous consent policy results in data being wrongly withheld | During this phase consent policies are likely to be simple and binary: to allow all data or no data in a given context. The potential for mistake is low, Policies will be applied by a system administrator who has been trained in the potential for impacting service availability. | Significant | Very Low | 1 |  |  |  |  | Significant | Very Low | 1 |  | All | Open
4.1 | Service is Non-Performant | In this mode of use, performance is critical to the user experience. Queries are executed synchronously, and the latency of the System of Systems directly impacts the usability of client software. | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians who are intolerant of poorly performant software will revert to previous methods. | poorly designed client software results in a concentration of service demand which impacts performance for other data consumers. | Application level monitoring tracks transaction round-trip time. A service desk is alerted if sustained round-trip times rises above a configurable level. Individual data consumers access rights can be suspended. Data consumers are only accepted as participants following an onboarding process which involves assuring the interactions between client software and the System of Systems. | Minor | High | 2 |  |  |  |  | Minor | High | 2 |  | All | Open
4.2 | Service is Non-Performant | In this mode of use, performance is critical to the user experience. Queries are executed synchronously, and the latency of the System of Systems directly impacts the usability of client software. | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians who are intolerant of poorly performant software will revert to previous methods. | a poorly performant data providers impacts overall System of Systems performance. | Connections form the System-of-Systems to data providers time out after a configurable period. The System-of-Systems inserts information into the result set returned to the data consumer detailing that data from particular data providers is not available. Client software can inform users that data is missing from potential sources. The regional FHIR Proxy has been performance tested on data volumes which are representative of those encountered at a major care setting. Response times for typical queries are in the order of 200ms on moderately sized server (4 core). | Minor | High | 2 |  |  |  |  | Minor | High | 2 |  | All | Open
4.3 | Service is Non-Performant | In this mode of use, performance is critical to the user experience. Queries are executed synchronously, and the latency of the System of Systems directly impacts the usability of client software. | Use of the System-of-Systems is limited to 5 participants with point to point data access requirements. The information available is new to clinicians and established care practises have operated until recently without access to regional data. Clinicians who are intolerant of poorly performant software will revert to previous methods. | cumulative demand from all data consumers exceeds capacity of System of Systems | The System-of-Systems has been sized to support the known use cases of the 5 pilot participants. The System-of-Systems has been stress tested to prove support for a sustained demand of 10 queries per second. The System-of-Systems is hosted on a virtualised environment and the solution has been architected to efficiently utilise available CPU cores. Subject to software license considerations, the platform can be scaled fluidly. | Minor | Low | 1 |  |  |  |  | Minor | Low | 1 |  | All | Open
5.1

## 3 Subscriptions
Hazard | [5 empty] | Initial Risk Rating |  |  | Additional Controls |  |  |  | Residual Hazard Risk Rating
Num | Hazard Name | Hazard Description | Potential Clinical Impact | Possible Causes | Existing Controls | Consequence | Likelihood | Risk | Design | Test | Training | BPC | Consequence | Likelihood | Risk | Summary of Actions | Owner | Status
9.1 | Service is Unavailable, or Access is Denied | New subscriptions cannot be registered by data consumers. Data providers are unable to send notification of an event matching a subscription | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | a hardware or software fault results in system unavailability | Software components are hosted in a virtualised environment on hardware with inbuilt redundancy. The hypervisor provides for high availability and will automatically re-instantiate non-functional components. Components are monitored and a service desk automatically informed of a range of conditions. Service availability could be monitored using an external arbiter if a use case were to justify it. Faults are logged and it is possible to establish the root cause of a failure. | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
9.2 | Service is Unavailable, or Access is Denied | New subscriptions cannot be registered by data consumers. Data providers are unable to send notification of an event matching a subscription | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | : data is corrupted through faulty disks or a software error to an extent that is causes a loss of service. | Components are designed to be stateless where possible with few dependencies on data. Exceptions are configuration data, the master patient index, consent policies, master records for patient, practitioners and organisations. A copy of configurations is held in a source control repository and other data is backed up daily. A backup can be restored within two hours. Master data can be recreated by replaying messages from participants and other sources. In particular, subscription data can be recreated by querying the subscription resources from the providers. | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
9.3 | Service is Unavailable, or Access is Denied | New subscriptions cannot be registered by data consumers. Data providers are unable to send notification of an event matching a subscription | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | a DNS, firewall configuration change or a certificate revocation denies access to an individual participant | Firewall and certificate changes are controlled by a Change Advisory Board. Certificate signing and revocation is software controlled and audited. Only privileged system administrators can revoke a certificate. Mutual TLS authentication is not operational. A participant will not be denied access because of a DNS entry. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
9.4 | Service is Unavailable, or Access is Denied | New subscriptions cannot be registered by data consumers. Data providers are unable to send notification of an event matching a subscription | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | : a software update introduces a fault | Software changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan. Software is subjected to continuous integration testing which highlights regressive behaviour. Software source code is maintained in a public source code repository. Problematic changes can be easily backed out. | Significant | High | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Significant | High | 3 |  | All | Open
9.5 | Service is Unavailable, or Access is Denied | New subscriptions cannot be registered by data consumers. Data providers are unable to send notification of an event matching a subscription | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | planned maintenance results in downtime | Maintenance is controlled by a Change Advisory Board Any maintenance requiring downtime will be scheduled outside of peak operational hours | Minor | Very High | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Minor | Very High | 3 |  | All | Open
10.1 | Subscription and related data is corrupted | Data provided via the System-of-Systems through the subscription mechanism to a data consumer is not reflective of data supplied by data providers. | Use cases are targeted to process improvement rather than informing clinical decisions. Data corruption might lead to inefficiencies in clinical processes but will have low impact on patient safety. | a software fault corrupts FHIR resources delivered through a subscription notification. | Model consumer software, as developed by the YHCR, validates the structure of FHIR resources and rejects an attempt to deliver a subscription notification with an invalid payload. The System-of-Systems logs and monitors consumer responses and operators are promptly informed of failed delivery attempts. Subscription notifications use the same processing pathway as the much higher volume synchronous query pattern. The same validation is possible, and any software faults are likely to manifest themselves initially through user interfaces used for direct care. Software is coded to a design which minimises manipulation for resource content to a few essential operations. | Significant | Very Low | 1 |  |  |  |  | Significant | Very Low | 1 |  | All | Open
10.2 | Subscription and related data is corrupted | Data provided via the System-of-Systems through the subscription mechanism to a data consumer is not reflective of data supplied by data providers. | Use cases are targeted to process improvement rather than informing clinical decisions. Data corruption might lead to inefficiencies in clinical processes but will have low impact on patient safety. | a software fault corrupts FHIR subscriptions distributed to data providers | General corruption to the structure of the FHIR resource will be detected by the receiving data provider. The model FHIR proxy validates resource structure and rejects an attempt to create an invalid subscription. The System-of-Systems logs, and monitors consumer responses and operators are promptly informed of failed delivery attempts. Corruption of the FHIR search path is possible and may lead to inoperable subscriptions or incorrect event notifications. Software units that manipulate search paths are tested using test plans based on pilot use cases. Corruption can be automatically rectified by revoking the original subscription and replaying the subscription made with the System of Systems | Significant | Very Low | 1 |  |  |  |  | Significant | Very Low | 1 |  | All | Open
11.1 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | an incorrect misconfiguration of the participant registry associates a logical provider identity with a different provider’s endpoint address. As a consequence, subscriptions are registered with the wrong provider | Configuration changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan. Automated implementation testing using messages containing synthetic data can ensure routing of messages is correct. The same endpoint address will be used for subscriptions as for synchronous query. Mis-registration will be apparent during the onboarding process. | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
11.2 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | a misconfiguration of the provider registry records an invalid endpoint address. As a consequence, subscriptions are not registered | Outgoing subscriptions are processed from a persistent message queue. An invalid endpoint address would cause the dispatching process to error and for the message to be suspended. Monitoring software alerts operators of the error, the endpoint address will be corrected, and service resumed without data loss. | Significant | Low | 2 |  |  |  |  | Significant | Low | 2 |  | All | Open
11.3 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | : a misconfiguration at a data provider causes the data provider to register their patient contact with a different provider. As a consequence patient centric subscriptions are registered with the wrong provider | An onboarding process validates that that PIX registrations are being made correctly at the point of go-live. | Significant | High | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Significant | High | 3 |  | All | Open
11.4 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | an operator erroneously or maliciously corrupts PIX data. As a consequence, patient centric subscriptions are not registered with providers | Database access is restricted to small number of administrators with individual login credentials. Database operations are audited, and audit records are periodically reviewed by an independent supervisor who does not have database administration privileges | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
11.5 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | : a data provider registers a new patient contact with the System of Systems. A software error prevents patient-centric subscriptions for the patient being dispatched to the provider. | Software development is test led. Automated tests validate PIX processing and specifically the issuance of subscriptions based on new patient contact. | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
11.6 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | a software fault leads to subscription results being lost in transit | Software development is test led. Automated tests prove operation of message pathways responsible for delivering subscription results. Audit records are written of all subscription results received and dispatched. A fault can be detected and diagnosed. Software logs record all processing data processing errors. An operator is autromatically alerted of all logged errors. Should an error be identified then Service Management ITIL processes are followed to formalise incident reporting and resolution through to software delivery and fix. | Significant | Medium | 2 |  |  |  |  | Significant | Medium | 2 |  | All | Open
11.7 | Subscriptions or notifications are lost in transit | Subscriptions are either not dispatched by the System-of-Systems to relevant data providers or subscription results are not returned to subscribing data consumers. The effect being that the notifications which are expected by a data consumer do not arrive. Patient-centric subscriptions should be dispatched to all data providers who have registered contact with the patient with the System of Systems. Other subscriptions should be dispatched to all data providers. Any deviation from this rule is incorrect behaviour and will result in lost data. Subscription results received by the System-of-Systems should be dispatched to all data consumers making the subscription. | Use cases are targeted at process improvement rather than informing clinical decisions. Incorrect subscription dispatch will result in events not being communicated to data consumers. This might lead to inefficiencies in clinical processes but will have low impact on patient safety. | data consumer endpoint is unavailable | Automated monitoring software provides notification of endpoint unavailability and queue levels to technical staff for action. Support staff work with appropriate data consumer technical representatives to resolve. Message queues are persisted. No data loss results from a failure to dispatch a notification. | Minor | High | 2 |  |  |  |  | Minor | High | 2 |  | All | Open
12.1 | Service is Non-Performant | Subscriptions are inherently asynchronous in nature and so some delay between an event occurring and subscriber being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for subscription delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences. Of particular concern is poor performance which causes subscription throughput to fall below the rate at which subscription or notifications are delivered to the System-of-Systems for processing for an extended period of time. Such a situation could overload the service, disrupting service availability for an extended period of time and potentially impacting other modes of use | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | poorly designed message pathway configuration results in a bottleneck at a particular processing step | The software is performance tested. The pilot use cases are well understood, and the software can be tested with use cases which accurately reflect actual usage. It is unlikely that novel processing requirements will be encountered in live operation. The message pathway is configured as a series of independent components. A poorly performing component results is a message queue building up. The queue is persistent, and no message loss will occur. Monitoring software tracks message queue sizes. A service desk is alerted if sustained queueing rises above a configurable level. Message deliveries to endpoints are not guaranteed to be in order (e.g. sequential streams). Message queues can be processed by components operating in parallel to improve throughput. Message delivery configuration settings (e.g. Connection timeouts, retry settings) can be altered to achieve optimal throughput. The computing resources allocated to each component can be altered to remove bottlenecks. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
12.2 | Service is Non-Performant | Subscriptions are inherently asynchronous in nature and so some delay between an event occurring and subscriber being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for subscription delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences. Of particular concern is poor performance which causes subscription throughput to fall below the rate at which subscription or notifications are delivered to the System-of-Systems for processing for an extended period of time. Such a situation could overload the service, disrupting service availability for an extended period of time and potentially impacting other modes of use | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | : an individual subscription source floods the service with, possibly, incorrect subscriptions or notifications | Pilot use cases are well understood with predictable transaction volume. Unusually high transaction volumes are likely to indicate a fault at a data provider or consumer. If queuing thresholds are exceeded, then system operators are informed via monitoring software and can limit access to the inbound organisation that is causing the flood of inbound messages until the fault has been corrected | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
12.3 | Service is Non-Performant | Subscriptions are inherently asynchronous in nature and so some delay between an event occurring and subscriber being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for subscription delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences. Of particular concern is poor performance which causes subscription throughput to fall below the rate at which subscription or notifications are delivered to the System-of-Systems for processing for an extended period of time. Such a situation could overload the service, disrupting service availability for an extended period of time and potentially impacting other modes of use | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | cumulative demand by all subscription sources exceeds capacity of System of Systems. | The System-of-Systems has been sized to support the known use cases of the 5 pilot participants. The System-of-Systems is hosted on a virtualised environment and the solution has been architected to efficiently utilise available CPU cores. Subject to software license considerations, the platform can be scaled fluidly | Minor | Low | 1 |  |  |  |  | Minor | Low | 1 |  | All | Open
12.4 | Service is Non-Performant | Subscriptions are inherently asynchronous in nature and so some delay between an event occurring and subscriber being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for subscription delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences. Of particular concern is poor performance which causes subscription throughput to fall below the rate at which subscription or notifications are delivered to the System-of-Systems for processing for an extended period of time. Such a situation could overload the service, disrupting service availability for an extended period of time and potentially impacting other modes of use | There are only a few use cases among the pilot organisations which rely on subscriptions. Of these only one is time critical: notification to a metal health care team that a ‘frequent-flyer’ has contacted 111 or 999. The impact of a subscription notification not reaching the care team has low clinical impact: a patient is unnecessarily attended to by an ambulance. Non-time critical subscription usage is not impacted so long as data is not lost due an outage and the outage is resolved within a few hours. | : a denial of service attack reduces capacity available for legitimate users | Access to the service is restricted to HSCN. The service is hosted at a major NHS Acute Hospital with infrastructure designed to meet its obligation under the EUs Network and Information Security Directive and specifically includes firewalls designed to withstand denial of service attacks. Identity and access management security has been designed to allow legitimate transactions to be easily distinguished from illegitimate ones with substantial processing. | Minor | Very Low | 1 |  |  |  |  | Minor | Very Low | 1 |  | All | Open

## GPC
[7 empty] | Initial Risk Rating |  |  |  | Additional Controls |  |  | Residual Hazard Risk Rating
Hazard number (as per GPC HL) | Hazard type | Hazard name | Hazard description | Potential clinical impact | Possible causes | Existing Controls | Consequence | Likelihood | Risk | Design | Test | Training | BPC | Consequence | Likelihood | Risk | Summary of Actions | Owner | Status
3 | HTML | The HTML view headings are not directly aligned to the Professional Record Standards Body (PRSB), CRE or other professional standard headings | The specification may not match existing standards or record structures - for example, PRSB standards, Summary Care Record, or other systems where section headings have an agreed and/or widely used format. Some users will be using GP Connect alongside or in addition to the Summary Care Record. There are a number of differences to the way each application displays the data. This could result in user confusion. | Clinical information may be presented in an unfamiliar order or under an unexpected heading. This may lead to important clinical information being missed, leading to a delay to the assessment/treatment of the patient, and potentially inappropriate care. A clinician may misunderstand the layout of the section headings as they are not aligned with the PRSB headings. This could make the data more difficult to interpret, which may cause an incorrect diagnosis with subsequent delay or incorrect treatment. | There is no universal standard to align to and it is difficult to choose one of the standards that are available. There are no common data models in primary care systems. | HTML views are only one component of the medical record which is available from the System of Systems which offers a blend of data from different systems at different levels of maturity. Data consumers are expected (and are assured as doing so by the YHCR) to present data in a manner informs clinicians in variances in compliance with PRSB and other standards. | Significant | Medium | 2 | The GP Connect Adapter maps HTML views to DocumentReferenc FHIR resources which are coded to regionally standardized SNOMED-CT codes. Data consumers are able to use the coding standards to present the views in a context which is clear to clinicians and avoids. |  |  |  | Significant | Low | 2 |  | RW | Transferred
11 | General risk | Consuming system misunderstands detail for data sent from providing systems | The data held in GP systems can be complex and detailed. There is a risk that consuming systems could misunderstand data that they receive. | If the consuming system is not designed in a way that fully considers the detail of the data, then it may not display it to the clinician in a way that is clear and appropriate. | Examples: 1. The structure of the investigations data returned by GP Connect is complex. It can contain comments against different levels of the report. 2. GP Connect 'allows' a consumer of data to request the medications without all the issues. | Assurance process for data consumers examine presentation of data with a particular focus on the blending of data from different sources results in a consonsistent oresentation of clinical facts. | Significant | Medium | 2 | Structured data from GP Connect will be converted by the GP Connect adapter to a regionally agreed FHIR profile for the concept being sourced. DADA will determine the concepts which are safe to releasethrough consideration of their alignment to profiles in use for data available from other data providers | Assurance of consumers will explicitely validate acquisition of data from GP Connect and will ensure that where GP Connect data is blended with data from other sources that it is correctly represented. |  | Data pairings between data providers and consumers in the System of Systems will by default exclude acesss to the GO Connect data source. Pairings will only be openned up on completion of an assurance process. | Significant | Low | 2 |  | RW | Transferred
16 | Structured - General | Modular design of GP Connect profiles | Profiles can be requested separately in Access Record Structured. This gives flexibility for consuming systems and enables bespoke development to provide an efficient and effective product for the end-user. However, there is a risk that the consuming system may not pull in all the information necessary for safe and effective patient care - for example, it may call the medicines profile but not the allergies one. | Missing information may lead to possible incorrect diagnosis and treatment. | Requesting the wrong levels of detail for medications. Requesting the inappropriate 'clinical area' (logical sections of GP systems) - for example, requesting medications without allergies. |  | Considerable | Medium | 3 |  | Assurance of consumers will verify that all dependent informtion (from any data provider) is presented at the same time to a clinician |  |  | Considerable | Low | 2
18 | Structured - General | Data without context can be misinterpreted | Uncategorised data seen in isolation from associated categorised data could be incorrectly interpreted. | The clinician may interpret incorrect information to come to a possible incorrect conclusion. | Requesting uncategorised data where linked data is not displayed. Consumers don’t know how to display this data to their users or users don’t understand the types of information displayed in this category. Examples: 1. Free text is used to indicate whether the patient is lying down, sitting or standing during a blood pressure reading. Code: Blood pressure 140/80 Text: lying down Code: Blood pressure 160/90 Text: sitting 2. Free text is used to indicate the three separate readings of a patient's peak flow test (asthma). Code: Peak Flow Text: Reading 1 540 Reading 2 560 Reading 3 550 |  | Considerable | Medium | 3 | The provenance of all FHIR resources is tagged in the meta data of the resource and consumers will have the necessary information to present the data in context | Assurance of consumers will verify that data from any data providers is presented in context. |  |  | Considerable | Low | 2
19 | Structured - General | Risk of duplication due to sharing | If a consumer is trying to import structured data from GP Connect there is a risk that some of the data may already be in that system and this might cause duplication. | The clinician may interpret incorrect information to come to a possible incorrect conclusion | Consuming system makes a similar call to GP Connect as it has previously - for example, meds reconciliation after more than one hospital admission. | Data from GP Connect is aggregated with data from all other data providers from the YHCR and the presence of duplicated data is a well anticipated matter. Consumers will be designed with consideration of de-duplication. | Significant | Medium | 2 | Data which is reliably identifiable as a duplication of data available elsewhere from the YHCR will be withheld by the GP Connect Adapter (ie: pathology test results)., | Assurance of consumers will verify that duplicated data is appropriately removed. |  |  | Significant | Low | 2 |  | RW | Transferred
21 | Structured - General | Data content inconsistency | . Multiple data sources all provide the same or similar data elements in varying formats, which means the specification may not match the content of source system. Examples: 1. Some data sources may not be compliant with mandatory value set descriptors. 2. There may be inconsistencies with headings and descriptions in documents and referrals. 3. The interpretation of the specification by third parties may vary, leading to differences between specification intention and implementation. | Multiple variations in data content or an inconsistent use of terms may lead to difficulties in the interpretation of the record. Use of non-standard terms, local abbreviations or codes that are unfamiliar to systems using these data items, and users interacting with those systems may result in delayed or inappropriate care. | Lack of standardisation of the HTML structure and content of data across systems' suppliers. | Data from GP Connect is aggregated with data from all other data providers from the YHCR and data inconsistency is a well anticipated matter. Data consumers will be designed to help clinicians resolve inconsistencies | Considerable | Medium | 3 |  | Assurance of consumers will verify that they are designed to help clinicians interpret potentially conflicting data. A YHCR capability which is under design will allow clinicians to annotate data from any source with qualifications in its reliability |  |  | Considerable | Low | 2 |  | RW | Transferred
31 | Structured - General | Local warnings not currently shared in GP Connect | Local warnings that may have been added at the patient's registered practice may not be shared via GP Connect - for example, patient has previously been abusive with reception staff. | The clinician may not have access to essential information that may affect the care and communication with the patient. | Not been covered as part of phase1 of GP Connect. |  | Minor | Medium | 2 |  |  |  | Users of all YHCR data consumers will be trained in the interpretation of data available from the YHCR and incompleteness is an inherrent factor which must be understood when using an aggregated medical record | Minor | Medium | 2
32 | Structured - General | Data marked as private is not shared | Data marked as private is not shared via GP Connect. | The clinician may not have access to important information that may affect the care of the patient. | Privacy for patients |  | Significant | Low | 2 |  |  |  | Users of all YHCR data consumers will be trained in the interpretation of data available from the YHCR and incompleteness is an inherrent factor which must be understood when using an aggregated medical record | Significant | Very Low | 1 |  | RW | Transferred
33 | Structured - General | Misunderstanding that consultations do not represent the whole patient record (have not defined how to request the whole record) | If a subset of the record is requested the clinician may not be aware that the rest of the record is available. | The clinician may not have a full picture of the previous care of the patient. | Poor consumer system design |  | Significant | Medium | 2 |  | Assurance of consumers will verify the completeness of data. |  |  | Significant | Low | 2 |  | RW | Transferred
36 | General risk | Technical issues delaying sharing of information | Patient diagnosis or treatment is delayed because some of the patient data is not available as a result of technical issues. | The clinician may not realise that the whole record is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe - for example, if they prescribed medication that interacts with another drug that was recently prescribed, but was not part of the record returned. The clinician may not realise that the whole record is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe. For example, medication is prescribed that interacts with another drug which was recently prescribed but was not part of the record returned. | The providing system fails to provide all of the relevant data for the API call. There may be some loss of data in the transit from the provider to the consumer. The consuming solution may not correctly display all the information contained in the message. The consuming system interprets data in an inconsistent or incomplete way across all providing systems. | Data impairments inserted into search results from the YHCR will inform the data consumer of techical difficulties in acquiring data. | Considerable | Medium | 3 |  | Assurance of consumers will verify that data impairements are correclty interpretted and clearly made available to clinicians. |  |  | Considerable | Low | 2 |  | RW | Transferred
38 | General risk | Patient data is missing from the patient record in the GP system due to non-technical issues | Although GP patient records have the best consolidated view of the patient's medical history, there will always be gaps. | The clinician may not realise that the complete patient history is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe. Some examples include: 1. System misleads a user into prescribing/administering an incorrect medication due to incomplete allergy/adverse reaction record on the GP system. 2. Patient is prescribed/administered incorrect medication whilst could cause deleterious effects, trigger an allergy or worsen a clinical condition. | This is a general scenario in which the GP isn't aware of the patient's full medical history. | The YHCR will assemble a medical record from all available sources. Information not available in the GP system may be available from an alternative source. | Significant | Medium | 2 |  |  |  | Users of all YHCR data consumers will be trained in the interpretation of data available from the YHCR and incompleteness is an inherrent factor which must be understood when using an aggregated medical record | Significant | Low | 2 |  | RW | Transferred
42 | General Risk | Patient chooses to not share some or all data outside the practice | GP Connect will not provide data where a patient has said they do not want to share their data outside of their GP practice or back to the registered practice in a federated clinic appointment scenario. GP Connect has no ability for a clinician to override this decision. Examples of clinical scenarios: 1. In A&E where the patient is asked to share data and changes their mind or where the patient is unconscious and there is a medical imperative the clinician does not have any power of override or patient seeking drugs of abuse does not want the contact and the prescription reported to the practice. This would currently not be visible to the practice in any way. 2. A sibling posing as the patient (knowing name, address, date of birth) and seeking medication. If part or all of the record isn't shared incorrect decisions can be made. | Patient diagnosis or treatment delayed. GP Connect is using the same model as SCR in that data will not be sent if the patient has recorded a dissent to share. This may lead to clinical safety issues which could have been avoided, for example, medication is prescribed to which the patient is allergic, has contraindications or a drug interaction. | This is a known outcome of the patient dissenting to share their data for the purposes of shared care in a direct care setting. |  | Significant | Low | 2 |  |  |  | Users of all YHCR data consumers will be trained in the interpretation of data available from the YHCR and incompleteness is an inherrent factor which must be understood when using an aggregated medical record | Significant | Very Low | 1 |  | RW | Transferred
43 | General risk | All of a patient's data is unavailable as a result of technical issues | There are a number of failure modes of the end to end transaction that could result in the consumer not receiving all of the GP record. For example, there is likely to be some downtime for GP Connect when a GP practice changes system provider. A new GP Connect endpoint cannot be set up at a provider until the old one is removed as the Spine will not know which is live when receiving a consumer request. | Patient diagnosis or treatment delayed due to clinician having to make decisions without the patient record being available. This may lead to clinical safety issues which could have been avoided, for example, medication is prescribed to which the patient is allergic, has contraindications or a drug interaction. | Any technical fault that prevents the end to end process succeeding. Examples: 1. If a number of messages fail and need to be resent then there is no technical mechanism to resend all messages. 2. When a practice switches supplier there is a period of time when the practice will lose GP Connect connectivity. This is due to the change in ASID that takes place when a practice switches supplier. As the SSP validates the ASID to allow transactions, when a practice gets a new ASID due to a supplier switch they are then rejected by the SSP. | Data impairments inserted into search results from the YHCR will inform the data consumer of techical difficulties in acquiring data. | Significant | Medium | 2 |  | Assurance of consumers will verify that data impairements are correclty interpretted and clearly made available to clinicians. | [6 empty] | RW | Transferred
44 | HTML | Absence of data | The absence of data due to being outside the scope of the HTML specification may cause an incorrect diagnosis with subsequent delay or incorrect treatment. Partial or full elements of the intended patient record are not adequately supported by the specification. | A healthcare professional may not be fully aware of required patient conditions, history or other key data elements. This may lead to delayed or inappropriate care. This may also result in an incorrect assessment being made if incomplete data elements are not detected. | The HTML scope does not cover the entire GP record. The specification does not include all patient record elements considered necessary to support effective health care. |  | Significant | Medium | 2 |  |  | Users of all YHCR data consumers will be trained in the interpretation of data available from the YHCR and incompleteness is an inherrent factor which must be understood when using an aggregated medical record |  | Significant | Low | 2 |  | RW | Transferred
46 | Structured - General | Date/time stamp of retrieval of medication/record from GP system is not presented to the end-user of the data | Where a consuming solution may import the structured data direct into a local solution and then persist or cache that data received from a GP system it is not clear what date and time the information was retrieved from the patient's record. The clinician does not know that this is not 'real time' data and therefore does not check that the medication information is still current and correct. | Clinician makes incorrect assumptions about what the patient is currently taking. If the patient is being seen as an outpatient they may have had a subsequent medication changed or prescribed which is not noted in the record that is persisted in the patient record. | The GP system does not send this information. This is known by the consuming solution from date and time information captured for audit and should be used to generate an entry and display in its solution. If this does not happen and the requirement to retrieve new data is not automated when a patient record is accessed in the consuming system the up to date information may not be displayed to the clinician. | Data is not cached by the YHCR. | Significant | Medium | 2 | Data served from the YHCR is timestamped at the point the the GP Connect interface is invoked. Systems which persist the data will have this timestamp available to present to the end user. |  |  |  | Significant | Low | 2
47 | HTML | Narrow search parameters | The amount of data that is returned to the clinician is controlled by the consuming solution. Information presented to clinician may be insufficient because of narrow search parameters supplied by the consuming solution. | The clinician may not realise that the whole record is not being displayed. If this is the case any decisions the clinician has to make could be potentially unsafe. For example, medication may be prescribed that interacts with another drug, which was recently prescribed but was not part of the record returned. | 1. Consumers hard coding or defaulting to narrow search criteria. 2. end-users applying incorrect/narrow search criteria. For example, only requesting the last week of a patient's medication history. |  | Significant | Medium | 2 |  | Assurance of consumers will verify the completeness of data. |  |  | Significant | Low | 2 |  | RW | Transferred
52 | Structured - General | Difference in rendering/presentation due to FHIR® standards framework mapping | Clinical context/meaning may be lost when the consumer creates their own render which is different from sender’s render - for example, the order of the document headings or the presentation of clinical content within each heading may vary between sender and consumer, and not be standardised across care settings. | This may lead to important clinical information being displayed incorrectly, which may cause delay to the assessment/treatment of the patient, and potentially inappropriate care. | Sending systems are not able to share their style sheet with consuming systems. No formally agreed default clinical presentation/user interface for displaying headings/content. | The YHCR DADA controld FHIR profiules in use in the region and ensures that the data content is completed and accurately reflects the context of data and it's interpretation on the carte setting that collected it. | Significant | Medium | 2 | Data is only releaserd from the GP Connect Adapter |  |  |  | Significant | Low | 2 |  | RW | Transferred
59 | General risk | Inconsistency between different supplier systems | Data content inconsistency between different supplier systems could make the data more difficult to interpret in the consuming system, which may cause an incorrect diagnosis with subsequent delay or incorrect treatment. | Difficulties in the interpretation of the record. Use of non-standard terms, local abbreviations or codes that are unfamiliar to systems using these data items, and users interacting with those systems may result in delayed or inappropriate care. | Provider systems structure their data content in different ways as there is no standardisation of content in the GP record. Despite the best intentions of all involved, suppliers may interpret the specification differently. No guidance on the definition, use or localisation of data items provided to those systems making use of the HTML view. | Data from GP Connect is aggregated with data from all other data providers from the YHCR and data inconsistency is a well anticipated matter. Data consumers will be designed to help clinicians resolve inconsistencies | Significant | Medium | 2 |  | Assurance of consumers will verify that they are designed to help clinicians interpret potentially conflicting data. A YHCR capability which is under design will allow clinicians to annotate data from any source with qualifications in its reliability |  |  | Significant | Low | 2 |  | RW | Transferred
61 | Structured - General | Proportional data gathering and data retention to support the clinician to navigate the patient record | The GP Connect Access Record Structured solution may, under some circumstances, return more patient data in response to a user’s query than is strictly necessary for the required purpose. The NHS currently has no clear policy on data return proportionality, making it difficult to make a 100% accurate judgement. | It may be difficult for a user to determine at the point of call all the data that may be required to appropriately treat a patient. Not having access to all of the patient record could lead to inappropriate or unsafe care being given. | Allowing a clinician to walk through the clinical record for the information they require to treat a patient may mean a large amount of patient data is taken via the API. | The FHIR based APIs supported by the YHCR allow consumers to traget data content precisely. | Significant | Medium | 2 | The GP Connect Adapter only returns the data items requested by the data consumer and filters out extraoneous data returned from the GP System. |  |  |  | Significant | Low | 2 |  | RW | Transferred

## 4 Transactional Messaging
Hazard | [5 empty] | Initial Risk Rating |  |  | Additional Controls |  |  |  | Residual Hazard Risk Rating
Num | Hazard Name | Hazard Description | Potential Clinical Impact | Possible Causes | Existing Controls | Consequence | Likelihood | Risk | Design | Test | Training | BPC | Consequence | Likelihood | Risk | Summary of Actions | Owner | Status
13.1 | Service is Unavailable, or Access is Denied | A data provider is either unable to connect to the System-of-Systems or their connection is rejected. The System-of-Systems cannot be used to dispatch a message or send an acknowledgement. The designation of the Systems of Systems transactional messaging pattern as unreliable places responsibility on participants to operate persistent message queues. If a message or acknowledgement cannot be dispatched via the System-of-Systems, then the message will be held by the dispatcher in a persistent queue and dispatch will be reattempted sometime later. Transient loss of service will cause a delay in message delivery but not message loss | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | a hardware or software fault results in system unavailability | Software components are hosted in a virtualised environment on hardware with inbuilt redundancy. The hypervisor provides for high availability and will automatically re-instantiate non-functional components. Components are monitored and a service desk automatically informed of a range of conditions. Service availability could be monitored using an external arbiter if a use case were to justify it. Faults are logged and it is possible to establish the root cause of a failure. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
13.2 | Service is Unavailable, or Access is Denied | A data provider is either unable to connect to the System-of-Systems or their connection is rejected. The System-of-Systems cannot be used to dispatch a message or send an acknowledgement. The designation of the Systems of Systems transactional messaging pattern as unreliable places responsibility on participants to operate persistent message queues. If a message or acknowledgement cannot be dispatched via the System-of-Systems, then the message will be held by the dispatcher in a persistent queue and dispatch will be reattempted sometime later. Transient loss of service will cause a delay in message delivery but not message loss | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | data is corrupted through faulty disks or a software error to an extent that is causes a loss of service. | Components are designed to be stateless where possible with few dependencies on data. Message data is transient, however historic data is backed up daily until retention rules mean data is purged. A backup can be restored within two hours. Message data can be recreated and replayed by replaying messages from provider sources | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
13.3 | Service is Unavailable, or Access is Denied | A data provider is either unable to connect to the System-of-Systems or their connection is rejected. The System-of-Systems cannot be used to dispatch a message or send an acknowledgement. The designation of the Systems of Systems transactional messaging pattern as unreliable places responsibility on participants to operate persistent message queues. If a message or acknowledgement cannot be dispatched via the System-of-Systems, then the message will be held by the dispatcher in a persistent queue and dispatch will be reattempted sometime later. Transient loss of service will cause a delay in message delivery but not message loss | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | a DNS, firewall configuration change or a certificate revocation denies access to an individual participant | Firewall and certificate changes are controlled by a Change Advisory Board. Certificate signing and revocation is software controlled and audited. Only privileged system administrators can revoke a certificate. Mutual TLS authentication is not operational. A participant will not be denied access because of a DNS entry | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
13.4 | Service is Unavailable, or Access is Denied | A data provider is either unable to connect to the System-of-Systems or their connection is rejected. The System-of-Systems cannot be used to dispatch a message or send an acknowledgement. The designation of the Systems of Systems transactional messaging pattern as unreliable places responsibility on participants to operate persistent message queues. If a message or acknowledgement cannot be dispatched via the System-of-Systems, then the message will be held by the dispatcher in a persistent queue and dispatch will be reattempted sometime later. Transient loss of service will cause a delay in message delivery but not message loss | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | a software update introduces a fault | Software changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan. Software is subjected to continuous integration testing which highlights regressive behaviour. Software source code is maintained in a public source code repository. Problematic changes can be easily backed out. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
13.5 | Service is Unavailable, or Access is Denied | A data provider is either unable to connect to the System-of-Systems or their connection is rejected. The System-of-Systems cannot be used to dispatch a message or send an acknowledgement. The designation of the Systems of Systems transactional messaging pattern as unreliable places responsibility on participants to operate persistent message queues. If a message or acknowledgement cannot be dispatched via the System-of-Systems, then the message will be held by the dispatcher in a persistent queue and dispatch will be reattempted sometime later. Transient loss of service will cause a delay in message delivery but not message loss | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | Planned maintenance results in downtime | Maintenance is controlled by a Change Advisory Board Any maintenance requiring downtime will be scheduled outside of peak operational hours | Minor | Very High | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Minor | Very High | 3 |  | All | Open
14.1 | Messages are Corrupted | Transactional data provided via the System-of-Systems to a data consumer is not reflective of data supplied by data providers. Transactions are typically used notify clinicians at one care setting of care provided at another. Corruption to the structure of data will likely render the transaction un-processable. Receiving systems will report an error and corrective action undertaken. More subtle corruption of data may be undetectable and lead to incorrect interpretation of the transaction | The 2 use cases of the first wave care are orientated to the provision of direct care and so any subtle corruption of data could result in inappropriate care being provided with serious clinical consequences. Structural corruption which leaves a transaction un-processable will impact the time critical use case severely and result in clinicians reverting to contingency processes. For non-time critical use cases there would be an opportunity to respond to the problem and correct the data but would add additional load on to clinicians | a software fault corrupts message content in transit | The message pathway for transactional messaging does not manipulate message content. The body of message is treated as an atomic unit and is delivered to a recipient in the form that it was received by the System of Systems. Corruption is unlikely. Sysstem testing has been targeted to testing known use cases. A service desk operates and will respond to issues encountered by message recipients. 24x7 support arrangements are in place. | Considerable | Medium | 3 | The organisational responsible for the DCB 0160 MUST apply some additional controls as detailed in the clinical safety report. |  |  |  | Considerable | Medium | 3 |  | All | Open
15.1 | Messages are lost in transit | Messages or acknowledgements are not dispatched to their intended recipients by the System of Systems. The failure my be transient, in which case the message or acknowledgement will be resent by its sender in accordance with the reliable messaging paradigm, or the failure may be systematic, in which case retry attempts are also lost. Transient failures appear to participants as though the System-of-Systems is non-performant and the hazard is considered in detail under D4. The clinical impact, controls and mitigations detailed here are for systematic failures | Pilot use cases are improvements to existing processes and fall back way of working exist. Sending systems are aware that a transaction has been lost: the reliable messaging paradigm requires messages to be acknowledged. Message loss is visible. | a misconfiguration of the defined message pathway in System of Systems. Most likely due to a software upgrade or problem with configuration management processes | Configuration changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan. Automated implementation testing using messages containing synthetic data can ensure routing of messages is correct. Guidance provided to data providers recommends that an operator informed of reported data delivery issues so allowing problems to be rectified in a timely manner. The System-of-Systems records and audit record for all messages received and dispatched. Lost messages can be traced. Automated tests ensure messages traverse System-of-Systems correctly and are delivered to their respective organisation endpoint. The message pathway in the System-of-Systems is componentised. Components draw messages from persistent message queues. A failure of a component results in que build up. Automated monitoring software alerts operators if a queue exceeds a configurable threshold. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
15.2 | Messages are lost in transit | Messages or acknowledgements are not dispatched to their intended recipients by the System of Systems. The failure my be transient, in which case the message or acknowledgement will be resent by its sender in accordance with the reliable messaging paradigm, or the failure may be systematic, in which case retry attempts are also lost. Transient failures appear to participants as though the System-of-Systems is non-performant and the hazard is considered in detail under D4. The clinical impact, controls and mitigations detailed here are for systematic failures | Pilot use cases are improvements to existing processes and fall back way of working exist. Sending systems are aware that a transaction has been lost: the reliable messaging paradigm requires messages to be acknowledged. Message loss is visible. | an incorrect misconfiguration of the participant registry associates a logical participant identity with a different participant’s messaging endpoint address. Consequently, messages are sent to the wrong provider | Configuration changes are controlled by a Change Advisory Board. All changes must be accompanied by a remediation plan. Automated implementation testing using messages containing synthetic data can ensure routing of messages is correct. The message header includes a recipient identifier. A correctly configured recipient message endpoint will reject the attempt to dispatch the message. The Systems of Systems would alert an operator. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
15.3 | Messages are lost in transit | Messages or acknowledgements are not dispatched to their intended recipients by the System of Systems. The failure my be transient, in which case the message or acknowledgement will be resent by its sender in accordance with the reliable messaging paradigm, or the failure may be systematic, in which case retry attempts are also lost. Transient failures appear to participants as though the System-of-Systems is non-performant and the hazard is considered in detail under D4. The clinical impact, controls and mitigations detailed here are for systematic failures | Pilot use cases are improvements to existing processes and fall back way of working exist. Sending systems are aware that a transaction has been lost: the reliable messaging paradigm requires messages to be acknowledged. Message loss is visible. | a misconfiguration of the participant registry records an invalid endpoint address. Consequently, subscriptions are not registered | Outgoing messages are drawn from a persistent message queue. An invalid endpoint address would cause the dispatching process to error and for the message to be suspended. Monitoring software alerts operators of the error, the endpoint address will be corrected, and service resumed without data loss. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
15.4 |  | Messages or acknowledgements are not dispatched to their intended recipients by the System of Systems. The failure my be transient, in which case the message or acknowledgement will be resent by its sender in accordance with the reliable messaging paradigm, or the failure may be systematic, in which case retry attempts are also lost. Transient failures appear to participants as though the System-of-Systems is non-performant and the hazard is considered in detail under D4. The clinical impact, controls and mitigations detailed here are for systematic failures | Pilot use cases are improvements to existing processes and fall back way of working exist. Sending systems are aware that a transaction has been lost: the reliable messaging paradigm requires messages to be acknowledged. Message loss is visible. | participant endpoint is unavailable | Automated monitoring software provides notification of endpoint unavailability and queue levels to technical staff for action. Support staff work with appropriate participant technical representatives to resolve. Message queues are persisted. No data loss results from a failure to dispatch a message | Minor | High | 2 |  |  |  |  | Minor | High | 2 |  | All | Open
16.1 | Service is Non-Performant | The service is inherently asynchronous in nature and so some delay between an event occurring at a data provider and a data consumer being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for message delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | poorly designed message delivery configuration results in a concentration of service demand such as message queueing which impacts performance for other data consumers | The software is performance tested. The pilot use cases are well understood, and the software can be tested with use cases which accurately reflect actual usage. It is unlikely that novel processing requirements will be encountered in live operation. The message pathway is configured as a series of independent components. A poorly performing component results is a message queue building up. The queue is persistent, and no message loss will occur. Monitoring software tracks message queue sizes. A service desk is alerted if sustained queueing rises above a configurable level. Message deliveries to endpoints are not guaranteed to be in order (e.g. sequential streams). Message queues can be parallel processed to ensure optimal delivery times. The computing resources allocated to each component can be altered to remove bottlenecks. | Minor | Medium | 2 |  |  |  |  | Minor | Medium | 2 |  | All | Open
16.2 | Service is Non-Performant | The service is inherently asynchronous in nature and so some delay between an event occurring at a data provider and a data consumer being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for message delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | Data providers flood inbound endpoints affecting overall System-of-Systems performance. | Pilot use cases are well understood with predictable transaction volume. Unusually high transaction volumes are likely to indicate a fault at a data provider or consumer. If queuing thresholds are exceeded, then system operators are informed via monitoring software and can limit access to the inbound organisation that is causing the flood of inbound messages. | Minor | Low | 1 |  |  |  |  | Minor | Low | 1 |  | All | Open
16.3 | Service is Non-Performant | The service is inherently asynchronous in nature and so some delay between an event occurring at a data provider and a data consumer being notified is to be expected. The delay that is acceptable depends on the use case to which the technology is applied. Terms of service for the System-of-Systems will be published and these will include a maximum latency for message delivery (within the boundary of responsibility and subject to performance of data consuming endpoints). This will be a key consideration for participants when designing services and it is reasonable to expect non-compliance to have significant consequences | The first wave pilots have 2 use cases for transactional messaging: • the delivery of a transfer of care from an ambulance to an emergency department; • the referral of a cancer patient from a secondary to a tertiary care provider. The first of these use cases is time sensitive in that the transfer of care should arrive in ED before the patient. Delay in dispatching the acknowledgement has no clinical impact. If the transfer of care does not arrive then the handover will follow existing procedures involving extracting a PDF from the ambulance system and uploading it to the ED system. This might result in a delay in care being provided to a patient in a critical condition. There will be no impact of a transient outage lasted less than a few hours for the second use case. | cumulative data provision by all data providers exceeds capacity of System of Systems | The System-of-Systems has been sized to support the known use cases of the 5 pilot participants. The System-of-Systems is hosted on a virtualised environment and the solution has been architected to efficiently utilise available CPU cores. Subject to software license considerations, the platform can be scaled fluidly | Minor | Very Low | 1 |  |  |  |  | Minor | Very Low | 1 |  | All | Open

## 5 Provider & Consumer Hazards
| Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[5 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
1 | Information exists in the provider system however it is not shared to the consumers as it is out of scope | Clinician at consuming site bases treatment on information provided but may be missing additional, vital information e.g. flags and alerts | Patient may be mis treated as all information is not visible at that time, the clinician may assume their clinical decision on the information only displayed | 1. Only data fields defined within the individuals scope specification are shared, this can vary for each organisation | This is personal to each provider and consumer, please decide if these Hazards are applicable and transfer to your own Hazard log, apply the design fetures and mitigate accordingly. | [5 empty] | The severity of the hazard cannot be scored as the severity will alter between sites/users. It is therefore the responsibility of the provider/consumer to evaluate the hazards based on their environment and uses of the system. |  |  |  | Additional Controls should be added by the provider/consumer, these should be relevant to your own organisation. | [5 empty] | The severity of the hazard cannot be scored as the severity will alter between sites/users. It is therefore the responsibility of the provider/consumer to evaluate the hazards based on their environment and uses of the system. |  |  |  | Rebecca Wilson | Transferred
2 | The consuming system pulls information from SoS relating to an incorrect patient | Clinician is viewing information for the incorrect patient | Incorrect patient information would provide the clinician with the wrong information and could lead to patient harm and/or death if treated according to the wrong information | 1. Providing system sends incorrect patient record to SoS- this would be due to human error as the providers will have been clinically assured | [20 empty] | Rebecca Wilson | Transferred
3 | Information outside of the specification is sent to SoS by provider | Clinician is able to view more data than allowed | Psychological harm/trauma to the patient | 1- The providing site has shared more data fields than originally agreed and these will not have been clinically assured by YHCR | [20 empty] | Rebecca Wilson | Transferred
4 | Consuming system does not receive requested data from SoS | Clinician is not able to view additional patient information | The clinician is unable to provide a full treatment plan for the patient and lower quality of care due to the information not been available | 1-This could be because the providing system has an error, SoS has downtime or the consuming sites connection is lost | [20 empty] | Rebecca Wilson | Transferred
5 | Consuming system receives incorrect information from SoS | Clinician bases treatment on incorrect record | Incorrect information could lead to patient harm and/or death | Corruption in message between SoS and Consumer- the data fields agreed should have been clinical assured by the YHCR so this is unlikely | [20 empty] | Rebecca Wilson | Transferred
6 | Consuming system displays information in a way that is confusing or unexpected | Clinician makes inappropriate treatment decision based on information provided | Terminology inconsistencies and the structure of the data could lead to confusion and misinterpretation and therefore cause harm to the patient | 1. consuming system display configuration is not aligned to same mapping structure as providing system | [20 empty] | Rebecca Wilson | Transferred
7 | Consuming system is unable to access the information despite there being an indication that the information exists | Clinician at consuming bases treatment on incomplete record | As data fields vary between sites various data will be displayed meaning they could be critical information held at one site that is not been displayed in comparison to the other sites that may be displaying that data field, this could lead to the clinician missing crucial information and miss treating the patient resulting in harm | 1-error when mapping data fields at the consuming site | [20 empty] | Rebecca Wilson | Transferred
8 | Information received by SoS from the provider is out of date | Clinician bases treatment on out of date information | Out of date information could lead to the clinician basing their judgment on the information and lead to the patient receiving the wrong treatment and/or level of care | 1. System Latency | [20 empty] | Rebecca Wilson | Transferred
9 | SoS received duplicated or conflicting information from from the various providers to one record. | Clinician bases treatment on incorrect information | Clinician treats patient incorrectly according to out of data information causing harm to the patient | 1. Various sites hold incorrect/out of date patient information in their local record | [20 empty] | Rebecca Wilson | Transferred

## 6 FHIR PDS Read Only
| Hazard Assessment |  |  |  | Initial Risk | [9 empty] | Residual Risk | [9 empty] | Owner | Status
No. | Hazard Description |  |  |  | Existing Controls | [5 empty] | Initial Risk Assessment |  |  |  | Additional Controls | [5 empty] | Residual Risk Assessment
[5 empty] | HIT Design |  | User Training |  | Business Process | [5 empty] | HIT Design |  | User Training |  | Business Process Change
| Effect | Hazard | Harm | Possible Causes | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification | Description | Evidence | Description | Evidence | Description | Evidence | Severity | Likelihood | Risk | Justification
PDSRO1 | False positive PDS search result returned (single result). On going care compromised due to wrong PDS information returned, impacting ability to 1. Use correct NHS Number 2. Send correspondance to target patient 'A' (Patient B sent Patient A's comms, Patient A sent nothing). 3. Access wrong information / services e.g. SCR, ERS 4. Access the wrong patient medical record a. Clinical decision based on wrong information b. Creation of confused record - Patient A's clinical information could be recorded within patient B' Electronic Clinical Record | Wrong Patient PDS record returned | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Potential delay to Patient care | Duplication of records: Where 2 or more numbers/records exist for the same patient. Confused Records: Where the NHS number is being used by more than one patient. Incorrect demographic data: Information entered in error by end user. | Please review alongside your organisations IT and IG Policies and apply the design fetures, training, business processes and mitigate accordingly. | [5 empty] | The severity of the hazard cannot be scored as the severity will alter between sites/users. It is therefore the responsibility of the provider/consumer to evaluate the hazards based on their environment and uses of the system. |  |  |  | Additional Controls should be added by the provider/consumer, these should be relevant to your own organisation. | [5 empty] | The severity of the hazard cannot be scored as the severity will alter between sites/users. It is therefore the responsibility of the provider/consumer to evaluate the hazards based on their environment and uses of the system. |  |  |  | Paul Warwick | Transferred
PDSRO2 | False negative PDS search result returned (single result). On going care compromised due to lack of PDS information, adversely impacting ability to 1. Confirm NHS Number 2. Send correspondance to patient 3. Access other services e.g. SCR, ERS | No Patient PDS record returned where one exists | Potential delay to Patient care Could lead to creation of duplicate record | [21 empty] | Paul Warwick | Transferred
PDSRO3 | Multiple PDS search results returned for user to view and select the correct record. On going care compromised due to wrong selection of PDS information, impacting ability to 1. Use INcorrect NHS Number 2. Send correspondance to target patient 'A' (Patient B sent Patient A's comms, Patient A sent nothing). 3. Access wrong information / services e.g. SCR, ERS 4. Access the wrong patient medical record a. Clinical decision based on wrong information b. Creation of confused record - Patient A's clinical information could be recorded within patient B' Electronic Clinical Record | Wrong selection of Patient PDS record | Potential for Patient A's information to be used / recorded against Patient B's record compromising both patients clinical record and care i.e. Confused record Potential delay to Patient care | [21 empty] | Paul Warwick | Transferred
PDSRO4 | Valid user (authorised ) and/or system fails to authenticate and / or authentication is delayed and/or authorise and therefore cannot retrieve patient details which impacts subsequent care | No Patient PDS record returned as Service can’t be accessed | Potential delay to Patient care | [21 empty] | Paul Warwick | Transferred

## Risk Matrix
Likelihood | Very High | 3 | 4 | 4 | 5 | 5 | Severity Classification | Interpretation | Number of Patients Affected
| High | 2 | 3 | 3 | 4 | 5
| Medium | 2 | 2 | 3 | 3 | 4 | Catastrophic | Death | Multiple
| Low | 1 | 2 | 2 | 3 | 4 |  | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Multiple
| Very Low | 1 | 1 | 2 | 2 | 3
|  | Minor | Significant | Considerable | Major | Catastrophic | Major | Death | Single
|  | Severity | [5 empty] | Permanent life-changing incapacity and any condition for which the prognosis is death or permanent life-changing incapacity; severe injury or severe incapacity from which recovery is not expected in the short term | Single
| Likelihood Category | Interpretation | [5 empty] | Severe injury or severe incapacity from which recovery is expected in the short term | Multiple
| Very high | Certain or almost certain; highly likely to occur | [5 empty] | Severe psychological trauma | Multiple
| High | Not certain but very possible; reasonably expected to occur in the majority of cases |  |  |  |  | Considerable | Severe injury or severe incapacity from which recovery is expected in the short term | Single
| Medium | Possible | [5 empty] | Severe psychological trauma | Single
| Low | Could occur but in the great majority of occasions will not | [5 empty] | Minor injury or injuries from which recovery is not expected in the short term | Multiple
| Very low | Negligible or nearly negligible possibility of occurring | [5 empty] | Significant psychological trauma | Multiple
[7 empty] | Significant | Minor injury or injuries from which recovery is not expected in the short term | Single
[8 empty] | Significant psychological trauma | Single
| 5 | Unacceptable level of risk | [5 empty] | Minor injury from which recovery is expected in the short term | Multiple
| 4 | Mandatory elimination of hazard or addition of control measure to reduce risk to an acceptable level | [5 empty] | Minor psychological upset; inconvenience | Multiple
| 3 | Undesirable level of risk. Attempts should be made to eliminate the hazard or implement control measures to reduce risk to an acceptable level. Shall only be acceptable when further risk reduction is impractical |  |  |  |  | Minor | Minor injury from which recovery is expected in the short term; minor psychological upset; inconvenience; any negligible consequence | Single
| 2 | Acceptable where cost of further reduction outweighs benefits gained or where further risk reduction is impractical
| 1 | Acceptable, no further action required