## Version Control
Version Number: | 2.4
Author (name) | Various
Name of approving committee | Interweave
Date Issued: | 10.08.23
9
Documents should be accessed via the Adoption Library on MS Teams to ensure the current version is used.
Updates
New Version Number | Date | Change
V1 | 13 September 2021 | Independent quality review of draft document to include consistency, branding changes and alignment to local ICS programme methods
V1.1 | 2022-02-04 | Rows 15, 16, 17 can be removed, product developments will be picked up as the projects are added to the planner
V2 | 22.04.22 | Amended document following ICS review.
V2.1 | 25.05.22 | The addition of assurance required from the Data Standards Manager before organisations can progress to Staging. This change will be implemented from 1 June 2022.
V2.2 | 25.05.22 | YHCR references removed from the document and replaced with Interweave.
V2.3 | 28.03.23 | Removal of requirement to request a sandpit tenancy for portal and S1 context launch consumption models.
| 28.03.23 | Removal of the requirement to carry out UAT in Sandpit for portal and S1 context launch consumption models.
V2.4 | 10.08.23 | YHCR references removed from the document and replaced with Interweave.
V2.5 | 11.10.23 | National Data Sharing agreement assurance activitiy added to the checklist.

## Checklist
Project:
Aha Ref: (where applicable)
Integrated Care System (ICS):
Go Live Target Date:
Initial Use Case:
Pilot Group: (if applicable)
|  |  | Go Live Approvers: | Interweave + consuming organisation approver (usually CCIO/CIO)
Go Live Recommendation
Activity | Check | Consumption Model | Organisation | Approver | Evidence | Status | Notes | Documents
Information Governance (IG)
| Interweave Information Sharing Agreement signed | All | consumer |  | Information Sharing Agreement - signed by the requesting organisations Caldicott Guardian |  | Agreement available from LTHT | Logged with IG team in Leeds
| Data Protection Agreement (DPA) signed | All | Consumer |  | Data Protection Agreement - signed by the requesting organisations Caldicott Guardian |  | Templates available from LTHT | Logged with IG team in Leeds
| Data Protection Impact Assessment Completed | All | Consumer |  | Consumer Organisation IG Lead decision on acceptance
| Fair processing materials in place | All | Consumer |  | Consumer Organisation IG Lead acceptance of appropriate amendment to fair processing material |  | Note section 3 of Communications Toolkit
| National Data Sharing Arrangement https://apply.ndsp.gpconnect.nhs.uk/ | All | Consumer |  | All organisations wishing to consume GP Connect data must sign the National Data Sharing Agreement and provide confirmation of this. An ASID will not be provided by NHSE without this.
Clinical Risk Assessment
| Clinical Safety Hazard Log | All | Interweave | Clinical Safety Officer | Consumer Organisation CSO sign off. Only required if bespoke consumption model.
| Clinical Safety compliance with 0160 | All | Consumer | Clinical Safety Officer | Consumer Organisation
Technical Assurance
| Tenancy request form submitted if bespoke consumption model. Tenancy requests in sandpit are not required for Portal or context launching from known systems. Tenancy requests for all consumption models are required for Production, and officers are advised to submit these early to ensure an ASID is provided by NHSD in time for progression to Production. Please note this is only relevant if GP Connect is requested. | All | Consumer | Hollie Harrison | Tenancy request raised in Jira |  | A requirement of NHSD
| NHS-D SCAL approved | GP Connect | Consumer | NHS-D | If organisation is not using the Interweave Portal.
| Interweave Architect Assurance approval | All | Interweave | Sophie Lowsley | Onboarding Technical Assurance Checklist
Cyber Security
| Interweave Cyber Lead approval | All | Interweave | Jason Creswell | Completed Onboarding Technical Assurance Checklist (tab 'Cyber') as well as an email from the Interweave Cyber Security Lead and Data Consumer Technical Lead confirming approval
Development & Testing
| Any errors with panel configuration / context launching patients etc. raised via Jira for investigation | Applicable to bespoke consumption models only. | Interweave
Business Readiness
| Confirmation of live data availability | All | ICS | ICS Project Manager |  |  | Refer to data dashboard
| Business change process agreement | All | Consumer |  | If data consumer end user processes are affected then evidence required that revised SOPs have been implemented. Email from operational manager to confirm acceptance. |  | AS IS / TO BE SOPs
| Business Readiness Assessment inc training needs and end users identified | All | Consumer |  | If end users are impacted by delivery then a readiness assessment should be attached authorised by the operational manager. |  | Could be pilot, who are the initial users, what are their training needs, when is the pilot scheduled, what is their commitment
| Communications Plan prepared and shared with Interweave Comms Lead | All | Consumer |  | If any external comms is planned then a Communication Plan authorised by provider, ICS and Interweave comms leads must be evidenced and this must be discussed with other involved parties (eg vendors) prior to implementation.
| Support Management Model in place | All | Consumer |  | User accounts in Jira for logging incidents. Support Model outline 1st Line Support mobilised Jira established Contact details provided (Contact details to be added / updated in onboarding or via a ticket logged in Jira) |  | Jira Service Desk URL required | Please review Interweave Core Service Support Overview
Executive sign off
| Has the executive sign off been received to allow progresssion. |  |  | Lee Rickles | If organisations are seeking remote approval to progress to the business readiness phase, then an email confirming their Executive is in agreement is required. |  | Executive approval email confirming they are happy for the organisation to progress to the next phase / all relevant steps have been completed. | Executive approval email confirming they are happy for the organisation to progress to the next phase / all relevant steps have been completed.
Actions Required before business readiness go live | Organisation |  | Actionee
Please review the Onboarding Assurance Quality Gate Approval Process | [7 empty] | Onboarding Assurance Quality Gate Approval Process
Note on D13: If not using YHCR portal please filter to All