## Provider Assurance Checklist
|  |  | Responsible Key: | Interweave Data Standards Team
Interweave PMO
Interweave Clinical Safety Officer
Provider
| SN | Task Description | Ops Stage | Responsible |  |  |  | Document Ref / Comments
|  |  |  | Project Team | Provider Org | Assurance Team | Clinical Safety Team
| 1 | Organisation Gate 1 approved | Gate 1 | P
| 2 | Upon being alerted to a new Provider project, Assurance Team to review the provider initation document within Jira / IOPS, which contains the proposed provider project details. | Not Started |  |  | P
| 3 | Obtain relevant provider organisation Tester(s) contact details, details to be added to the JIRA ticket. | Not Started | P
Initial Provider Meeting | 4 | Setup Intial meeting with Provider Organisation Tester(s) to discuss the following: | Not Started | P |  | P |  | PMO to liaise with Data Standards Team regards suitable dates.
|  | Data Assurance DA '- Within the meeting with the Provider, go through the FHIR resource(s) the organisation would like to provide. - Communicate the importance of aligning any identified FHIR resource(s) to the Interweave FHIR data standards. Point them to the following hyperlink: https://fhir.interweavedigital.com/ partiularly the 'Artifacts' section which details each Resource individualy. - Assurance Team to direct Provider Team to the Members Area and show them around, advsing that all documentaion needing for the Onboarding process will be available within this area. - Assurance Team to show Provider Team the Resource Mapping Documents and run through how they work, and our intentions with them. Provider can ask any questions they may have. - Explain / advise that they will need to map each of their chosen FHIR resource(s) data items (denoted within the 'Artifacts' section) to that of the corresponding data items within their local source system i.e. EPR fields. | Not Started |  |  | P |  | Interweave Implimentation Guide
|  | User Acceptance Testing UAT '- DA Team to advise how User Acceptance Testing (UAT) works and what will be requeired in terms of what the provider will need to send back to us in order to provide sufficient evidence to pass. - Point Provider Team towards the section within the Members Area that contains the Test Scripts for UAT. Advise that providers are also welcome to add there own to the downloaded file if they feel a scenario pertanent to them is missing, in order to enable to Provider Team to feel confident that all of the possible test scenarios / scripts have been thought of to allow them to be happy with the value of their own testing. - Scenarios tested should be based on the Resources the Provider is providing, and the organisation’s business workflow. | Not Started |  |  | P |  | Test Scenarios MASTER
|  | Test Patients Assurance Team to point Provider Team towards the section of the Members Area that can aid in the provision of a list of test patients to the Provider. Either via the link for 'Existing Interweave Test Patients' file OR via the process document link within 'New Test NHS Numbers' file . This will allow Providers to obtain test patients themselves. Test patients obtained via either method are to be registered once their development is completed. | Not Started |  |  | P |  | Existing Interweave Test Patients file
New Test NHS Numbers link file
|  | Interweave Console tool '- Assurance Team to advise Provider Team of the Interweave Console tool. Advise how they can check their data before sending for UAT / DA validation. - Assurance Team to advise Provider Team that they should raise a JIRA ticket if they do not have an account. - Assurance Team to advise Provider Team that they should use the tool to test their Resources, and ensure they are happy that they have passed all checks before they send the Data Assurance Report back for approval. | Not Started |  |  | P
|  | Returning UAT and DA Reports for Data Assurance Sign off - what is expected? User Acceptance Test '- Assurance Team to advise Provider Team that after Provider Team is statified internal testing is complete, the User Acceptance Test report should contain the list of test scenarios alongside corresponding screenshots from source system and portal along with relevant NHS numbers. This should be the evidence to them and us that the data being fed in, is coming as in the console as expected. Data Assurance - Assurance Team to advise Provider Team that the Resources they wish to be check for DA, should be returned by attaching the JSON files or the list of Test NHS numbers via the open Jira / IOPS ticket and tagging / emailing the Assurance Team of their return. |  |  | P | P
| 5 | Provider organisation Developers to internally develop their Resources. | Not Started/Sandpit - Assurance |  | P
| 6 | Assurance Team to provide continuous support to Provider organisation throught the development. | Not Started/Sandpit - Assurance |  |  | P
Provider Sandpit Testing | 7 | Comencement of Provider Testing | Sandpit - Assurance |  | P
|  | Provider to register multiple test patients (depending on the scenarios) on their organisation EPR/PAS. | Sandpit - Assurance |  | P
|  | - Provider to test against the Interweave FHIR data standards using the console validator tool and resolve any bugs or compliance issues before attemping / requesting assurance. | Sandpit - Assurance |  | P
|  | - Provider to carry out script testing that covers all workflows and scenarios identified for the resources they are providing. - Based on the scope for the FHIR Resource they are providing, Provider to validate that all relevant inputted data is displayed on the Interweave portal, and matched what is displayed in their PAS/EPR. | Sandpit - Assurance |  | P
|  | Provider to raise any portal / console issue(s) via Jira. | Sandpit - Assurance |  | P
|  | Assurance Team to provide continuous support to Provider organisation through the testing phase. | Sandpit - Assurance |  |  | P
|  | Provider to retest any / all issue(s) that failed tests and were then fixed . | Sandpit - Assurance |  | P
|  | - Provider to identifying any data quality issues on the back of both mapping and workflow scenario exercises. - Provider to include them and any problems / limitations and screenshots within the written Data Assurance Report. - Please note in some cases Clinical Safety may need to be involved dependant on the circumstances. | Sandpit - Assurance |  | P
|  | - After Provider Team is satisfied all testing activities have been completed as passed internally. Provider Team to create a User Acceptance report contaning everything denoted previously, and the Data Assurance JSON files / Test NHS numbers list. -The UAT and DA files will be sent to Assurance Team via the relevant open IOPS ticket. A subsequent email may be sent to natalee.pearson1@nhs.net and chintan.chokshi@nhs.net notifying that the Data Assurance files are ready for assurance checking / sign off. | Sandpit - Assurance |  | P
|  | Assurance Team to review provider organisation Assurance Reports (UAT and DA) and provide feedback / assurance outcome. Please note UAT and DA maybe well be approved in the first assurance review. If the Data Assurance Report fails however, Provider will need to recommence internal testing from the start of section 7. | Sandpit - Assurance |  |  | P
|  | Where continuous review and updating of Data Assurance Report is needed, this may be a calaboration between us and the Provider if clarity is needed from either side. Please note this step may not be needed if Asurance (UAT / DA) has been approved via the inital Data Assurance Report. | Sandpit - Assurance |  | P | P
| 8 | UAT & Data Assurance Report Approved | Sandpit - Assurance |  |  | P
| 9 | Clinical safety testing approved - Please note that data assurance and testing would have to be carried out again, if there are any JSON structural changes identified and added during clinical safety testing. |  |  |  |  | P
| 10 | Setup meeting with provider organisation test resources to discuss the following: | Staging - UAT | P
Staging |  | - Advise Provider Team to release the developed Resources into the Staging environment. - Advise Provider Team that the patinets need to be registered on PIX | Staging - UAT | P | P
|  | - Advise Provider Team about the consumer testing window for the newly developed resources. | Staging - UAT | P | P
| 11 | Provider org to carry out internal testing to validate the release in staging environment. |  |  | P
| 12 | Release to Live |  |  | P
| 13 | Clinical safety testing approved |  |  | P |  | P

## 3. Tester Contact Details
Name | Provider Organisation Name | Role | Telehone

## 4. Provider Review Meeting
Provider Name:
Number of Resources being provided:
Jira Ticket Number
Resource:
Resource:
Resource:
Resource:
Resource:
Resource:
Resource: