## Version control
Version | Author | Date
Vs1. | Hollie Harrison Interweave | 08.01.24

## Consumer - Interweave portal
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissons will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organsation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjets about how an organisation uses their personal data. |  | Links to website content etc.
National Sharing Agreement - if an organisation wishes to consume GP Connect data then they must sign up to the NSA. | National Data Sharing Arrangement for GP Connect - NHS Digital | Email confirming that the organisation has completed the NDSA - please note an approval email will not be shared by NHSE.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.
Complete tenancy form. | https://forms.office.com/e/ffU2NU5P9Q | Organisation.

## Consumer - CL (known)
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissons will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organsation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjets about how an organisation uses their personal data. |  | Links to website content etc.
National Sharing Agreement - if an organisation wishes to consume GP Connect data then they must sign up to the NSA. | National Data Sharing Arrangement for GP Connect - NHS Digital | Email confirming that the organisation has completed the NDSA - please note an approval email will not be shared by NHSE.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.
Complete tenancy form. | https://forms.office.com/e/ffU2NU5P9Q | Organisation.

## Consumer - Using own UI
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissons will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organsation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjets about how an organisation uses their personal data. |  | Links to website content etc.
National Sharing Agreement - if an organisation wishes to consume GP Connect data then they must sign up to the NSA. | National Data Sharing Arrangement for GP Connect - NHS Digital | Email confirming that the organisation has completed the NDSA - please note an approval email will not be shared by NHSE.
NHSE assurance
Supplier Conformance Assessment List (SCAL) - the organisation is responsible for completing this document, which is a technical document detailing the consumer supplier approach to information governance, clinical safety, functional testing and SMSP-PDS requirements. | Supplier Conformance Assessment List (SCAL) - NHS Digital | Confirmation that this document has been provided to you by NHSE - this will only be provided once they have assured the consumer supplier product as compliant with the SMSP- PDS specification for the relevant capabilities.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Testing
User Acceptance Testing - organisation to complete UAT and share findings with Interweave Test Team via Jira. |  | Confirmation from Interweave Test Team that the UAT has been approved.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.

## Consumer - CL (unknown)
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissons will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organsation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjets about how an organisation uses their personal data. |  | Links to website content etc.
National Sharing Agreement - if an organisation wishes to consume GP Connect data then they must sign up to the NSA. | National Data Sharing Arrangement for GP Connect - NHS Digital | Email confirming that the organisation has completed the NDSA - please note an approval email will not be shared by NHSE.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Witness Testing
Witness Testing - organisation to complete additional testing with Interweave Test Engineer to ensure the context launch is working as expected. This will be undertaken in Interweave Default Tenancy - access will have been provided by Interweave PMO following approval of Project Initiation Document. |  | Email approval received from Interweave Test Engineer.
Audit logging - if appropriate (organisation will be signposted by Interweave Test Engineer) Interweave Service Desk will review the audit logs to ensure tokens are being generated correctly. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.
Complete tenancy form. | https://forms.office.com/e/ffU2NU5P9Q | Organisation.

## Consumer - A2A
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjects about how an organisation uses their personal data. |  | Links to website content etc.
Witness Testing
Witness Testing - organisation to complete additional testing with Interweave Test Engineer to ensure the context launch is working as expected. This will be undertaken in Interweave Default Tenancy - access will have been provided by Interweave PMO following approval of Project Initiation Document. |  | Email approval received from Interweave Test Engineer.
Audit logging - if appropriate (organisation will be signposted by Interweave Test Engineer) Interweave Service Desk will review the audit logs to ensure tokens are being generated correctly. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.
Complete tenancy form. | https://forms.office.com/e/ffU2NU5P9Q | Organisation.

## Consumer - D2A
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjects about how an organisation uses their personal data. |  | Links to website content etc.
Witness Testing
Witness Testing - organisation to complete additional testing with Interweave Test Engineer to ensure the context launch is working as expected. This will be undertaken in Interweave Default Tenancy - access will have been provided by Interweave PMO following approval of Project Initiation Document. |  | Email approval received from Interweave Test Engineer.
Audit logging - if appropriate (organisation will be signposted by Interweave Test Engineer) Interweave Service Desk will review the audit logs to ensure tokens are being generated correctly. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.
Complete tenancy form. | https://forms.office.com/e/ffU2NU5P9Q | Organisation.

## Provider
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjects about how an organisation uses their personal data. |  | Links to website content etc.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Testing and Data Standards
Test Report - report and approved by organisation using test patients provided by Interweave - ensuring scenarios outlined in use case are available / working as expected, data is presently correctly etc. Successful report shared with Interweave Test Team for review / approval. |  | Email approval received from Organisation and Interweave Test Team.
Sample of FHIR resources - shared with Interweave Data Standards Team for approval. |  | Email approval received from Interweave Data Standards Team.
Data Quality Report - DQR produced by organisation detailing all tasks / activities completed by organisation and approved by Interweave Test and Data Standards Team submitted to Interweave Clinical Safety Officer for approval. |  | Email approval received from Interweave Clinical Safety Officer.
Health Check - organisation to request a health check is undertaken by Interweave Service Desk to ensure environments are running as expected. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.

## Provider - A2A
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjects about how an organisation uses their personal data. |  | Links to website content etc.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Testing and Data Standards
Test Report - report and approved by organisation using test patients provided by Interweave - ensuring scenarios outlined in use case are available / working as expected, data is presently correctly etc. Successful report shared with Interweave Test Team for review / approval. This will be undertaken in Interweave Default Tenancy - access will have been granted by Interweave PMO following approval of Project Initiation Document. |  | Email approval received from Organisation and Interweave Test Team.
Sample of FHIR resources - shared with Interweave Data Standards Team for approval. |  | Email approval received from Interweave Data Standards Team.
Data Quality Report - DQR produced by organisation detailing all tasks / activities completed by organisation and approved by Interweave Test and Data Standards Team submitted to Interweave Clinical Safety Officer for approval. |  | Email approval received from Interweave Clinical Safety Officer.
Health Check - organisation to request a health check is undertaken by Interweave Service Desk to ensure environments are running as expected. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.

## Provider - D2A
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjects about how an organisation uses their personal data. |  | Links to website content etc.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Testing and Data Standards
Test Report - report and approved by organisation using test patients provided by Interweave - ensuring scenarios outlined in use case are available / working as expected, data is presently correctly etc. Successful report shared with Interweave Test Team for review / approval. |  | Email approval received from Organisation and Interweave Test Team.
Sample of FHIR resources - shared with Interweave Data Standards Team for approval. |  | Email approval received from Interweave Data Standards Team.
Data Quality Report - DQR produced by organisation detailing all tasks / activities completed by organisation and approved by Interweave Test and Data Standards Team submitted to Interweave Clinical Safety Officer for approval. |  | Email approval received from Interweave Clinical Safety Officer.
Health Check - organisation to request a health check is undertaken by Interweave Service Desk to ensure environments are running as expected. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.

## Provider - TPP Non GP
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Information Governance
Information Sharing Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed ISA.
Data Protection Agreement - this document should be signed by both Interweave and the organisation. Once the project has been initiated, the organisation should liaise with Interweave Information Governance Team to create this document. |  | Signed DPA.
Data Protection Impact Assessment - organisation to complete a DPIA to identify risks arising from using Interweave products. The DPIA should help to negate risk and demonstrate the organisations compliance with GDPR. |  | Completed DPIA - responsibility of the organisation to ensure this is maintained.
Fair Processing Materials (Privacy Notice / Privacy Policy) - organisation to ensure documents are in place which provides information to data subjects about how an organisation uses their personal data. |  | Links to website content etc.
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Testing and Data Standards
Test Report - report and approved by organisation using test patients provided by Interweave - ensuring scenarios outlined in use case are available / working as expected, data is presently correctly etc. Successful report shared with Interweave Test Team for review / approval. |  | Email approval received from Organisation and Interweave Test Team.
Health Check - organisation to request a health check is undertaken by Interweave Service Desk to ensure environments are running as expected. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.
Please note the Staging environment is not available for TPP Non GP data provider projects.

## Data Maturity
Column1 | Column2 |  |  | Key:
Project: |  |  |  | Complete
IOPS reference: |  |  |  | On Track
Integrated Care System (ICS): |  |  |  | Outstanding
Go Live Target Date: |  |  |  | Escalate
Initial Use Case, if applicable:
Pilot Group, if applicable:
Go live approvers:
Go live recommendations:
The onboarding checklist should be submitted to Interweave PMO once all activities have been completed. Earlier submissions will be accepted if agreement has been granted by Interweave PMO to proceed without some of the activities being completed. If there are any questions relating to the process, then please contact Interweave PMO. Please note - preferred communication between organisation and Interweave is via Jira Service Desk - this ensures all communications are linked to the correct project.
Activity | Link to template / supporting information | Evidence | Status
Technical and Cyber Assurance
Onboarding Technical Assurance checklist - checklist completed by organisation and shared with Interweave Cyber Manager and Architect for approval. |  | Email approval received from Interweave Cyber Manager and Architect.
Testing and Data Standards
Test Report - report and approved by organisation using test patients provided by Interweave - ensuring scenarios outlined in use case are available / working as expected, data is presently correctly etc. Successful report shared with Interweave Test Team for review / approval. |  | Email approval received from Organisation and Interweave Test Team.
Sample of FHIR resources - shared with Interweave Data Standards Team for approval. |  | Email approval received from Interweave Data Standards Team.
Data Quality Report - DQR produced by organisation detailing all tasks / activities completed by organisation and approved by Interweave Test and Data Standards Team submitted to Interweave Clinical Safety Officer for approval. |  | Email approval received from Interweave Clinical Safety Officer.
Health Check - organisation to request a health check is undertaken by Interweave Service Desk to ensure environments are running as expected. |  | Email approval received from Interweave Service Desk.
Business Change
Business change processes - organisation to share Standard Operating Processes, User Guides, Comms plan etc., with Interweave or detail their plans to address this once the project progresses to Production to provide assurance to Interweave that the organisation is fully aware and ready to access the shared care record. |  | Links to documentation / plans for go live.
Support model - details of the organisation support model to be shared with Interweave. Organisation to ensure their key contacts detailed in the Onboarding Technical Checklist are up to date. |  | Details of support model to be shared. Key contacts are up to date - Interweave PMO to add these contacts to Interweave Console and end user comms page so Interweave Service Desk have access.
Approval
Onboarding Assurance checklist - organisation to share completed checklist with supporting evidence with Interweave PMO seeking approval to proceed to the next environment. Evidence should be embedded where possible into the document. Executive sponsor from the organisation should be in agreement for progression - the organisation should have an approval email confirming this. |  | Completed checklist with supporting evidence. Approval email from organisation executive sponsor.
Next steps:
Activity | Link to template / supporting evidence | Responsibility | Status
Notification shared with Interweave Service Desk of approval to proceed via Jira. |  | Interweave PMO.
Access Interweave Console to proceed to the next environment. |  | Organisation.